## IAG 2020-2026
Niagara Falls International Airport
Capital Improvement Program
Airport: | Niagara Falls International Airport |  |  |  |  | State: | New York |  |  | NPIAS #: | 0086 |  |  | LOC ID: | IAG | Date: | 2019-12-13
Project Description/Narrative |  | NPR | Work Code | Federal Funds ($1,000) |  |  |  |  | State Matching Funds ($1,000) | Local ($1,000) |  | State funded only | Totals ($1,000) | Environmental Type | Environmental Status | Comments
|  |  |  | Entitlement | Cargo Entitlement | Discretionary | State Apportion. | Supplementary Discretionary |  | PFC | Other
2020
Non-AIP Projects
Install Perimeter Fencing in Runway 10L Protection Zone, Design/Construction |  | N/A | N/A | [6 empty] | 109491.2 |  | 437964.8 | 547456 |  | Ongoing | NYSDOT AIR '99 & Future PFC
Wildlife Hazard Management Plan Update |  | N/A | N/A | [6 empty] | 83085 |  |  | 83085 |  | Approved 4/17 | PFC Application No. 3
Airfield Lighting and Signage, Construction |  | N/A | N/A | [6 empty] | 2916502 |  |  | 2916502 |  | Approved 6/18 | PFC Application No. 2
Snow Removal Equipment - Multi-Task Vehicle |  | N/A | N/A | [6 empty] | 159664 |  | 638656 | 798320 |  |  | Local share PFC Application No. 3
USAF Taxiway A Reconstruction |  | N/A | N/A
Total FY2020 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3268742.2 | 0 | 1076620.8 | 4345363
2021
Part 77 Off-Airport Land Easements/Acquisitions, Appraisals, and Obstruction Removal, 10L RW End |  | 80 | SP OT OB | 423000 |  |  |  |  | 23500 | 23500 |  |  | 470000 |  | Approved 9/17 | Carryover Passenger Entitlement Funds Local Share - Future PFC Application
Parallel Taxiway Program (Taxiway B, B1, B2, and Former E), Design |  | 75 | CA TW CO | 3453318 |  | 0 |  |  | 191851 | 191851 |  |  | 3837020 |  | Ongoing | Local Share - Future PFC Application
Rehabilitate Taxiway D, Construction |  | 74 | RC/RE TW IM | 427000 |  | 2897600 |  |  | 184700 | 184700 |  |  | 3694000 |  | Approved 2/19 | Carryover Passenger Entitlement Funds Local Share - Future PFC Application
Land Acquisition - RPZ for Runway 28 End |  | 67 | ST LA SZ |  |  | 0 |  |  | 0 | 0 |  |  |  |  | Future | Local Share - Future PFC Application
Non-AIP Projects
Snow Removal Equipment - Snowblower, Material Spreader | [9 empty] | 1475000 |  |  | 1475000 |  | Approved 2/17 | PFC Application No. 3
Total FY2021 |  |  |  | 4303318 | 0 | 2897600 | 0 | 0 | 400051 | 1875051 | 0 | 0 | 9476020
2022
Part 77 Off-Airport Land Easements, Appraisals, and Obstruction Removal Laur Road, 28R and 24 RW End |  | 80 | SP OT OB | 630000 |  |  |  |  | 35000 | 35000 |  |  | 700000 |  | Approved 9/17 | Local Share - Future PFC Application
Parallel Taxiway Program - Phase 1 (B1 to B2), Construction |  | 75 | CA TW CO |  |  |  |  | 11863341 | 659074.5 | 659074.5 |  |  | 13181490 |  | Ongoing | Local Share - Future PFC Application
Total FY2022 |  |  |  | 630000 | 0 | 0 | 0 | 11863341 | 694074.5 | 694074.5 | 0 | 0 | 13881490
2023
Part 77 Off-Airport Land Easements and Obstruction Removal 6 RW End |  | 80 | SP OT OB | 945000 |  |  |  |  | 52500 | 52500 |  |  | 1050000 |  | Approved 9/17 | Local Share - Future PFC Application
Total FY2023 |  |  |  | 945000 | 0 | 0 | 0 | 0 | 52500 | 52500 | 0 | 0 | 1050000
2024
Parallel Taxiway Program - Phase 2 (Remaining B), Construction |  | 75 | CA TW CO |  |  |  |  | Included in FY22 | [6 empty] | Ongoing | Local Share - Future PFC Application
Total FY2024 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025
Parallel Taxiway Program - Phase 3 |  | 75 | CA TW CO
Total FY2025 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026
Parallel Taxiway Program - Phase 4 |  | 75 | CA TW CO
Pavement Management Program (PCI Survey Updates) |  | 60 | PL MA MS
Total FY2026 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet2
Environmental type
Catex
Short EA
EA
EIS